## Action Tracker 2021
2021 NBAC ACTION TRACKER as of 9/24/2021
Priority Category | WBS | Action | Points of Contact | Due Date | Status | New/ Update | Legend: | Epic | Planned | In Progress | Complete | Past Due/Issue | Notes
1. NIEM 5.1 Minor Release | 1 | Release NIEM 5.1 NBAC, CMedlin
| 1.1 | Release 5.1 Issue Resolution | NBAC, Christina Medlin | 2021-02-01 | In Progress
| 1.2 | Alpha 1 Release | NBAC, Christina Medlin | 2021-01-01 | Complete | [7 empty] | Biometrics domain added new DNA content, Cyber domain added new content supporting the Federal Incident Reporting Requirements (FIRR), Emergency Management domain added flood damage claim content from OpenFEMA, Military Operations domain added cyber related content from the Joint Non-Kinetic Effectiveness (JNKE) IEPD. Link-http://niem.github.io/niem-releases
| 1.3 | Alpha 2 Release | NBAC, Christina Medlin | 2021-06-30 | Complete | [7 empty] | Updated the new DNA content in Biometrics, added and updated content to support SLTT agency Cyber Incident Reporting Requirements (CIRR) in Cyber, moved Justice code elements with a NCIC data type to the NCIC namespace, updated CUI codes, and fixed a truncated definition in Human Services.
| 1.4 | Beta 1 Release | NBAC, Christina Medlin | 2021-07-31 | Complete
| 1.5 | RC1 | NBAC, Christina Medlin | 2021-08-31 | Planned | Update
| 1.6 | Release | NBAC, Christina Medlin | Fall 2021 | In Progress | Update
| 1.7 | MOMS | NBAC, Christina Medlin | Q1 CY 2022 | Planned
2. Advance NIEM Adoption | 2.1 | US Bureau of Reclamation (USBR) Dept of Interior | Andrew Marquardt, RO'Connell
| 2.1.1 | Provide NIEM Training to US Bureau of Reclamation | Andrew Marquardt, Webb Roberts, RO'Connell | Revisit 2021 | Close Action | No response from USBR | [6 empty] | Emailed twice no response
| 2.2 | Statistics Domain | Chris Carrino, SSullivan
| 2.2.1 | Acquire content for technical review | Chris Carrino, SSullivan | 2021-02-16 | Complete
| 2.2.2 | Coduct Technical Review | Chris Carrino, Christina Medlin | 2021-04-15 | In Progress
| 2.2.3 | Incorporte content in Release 5.1 | Christina Medlin | 2021-06-30 | In Progress
| 2.2.4 | Provide Domain Onboarding Artifacts to USCB (DSA template, POA7M strawman, How to docs, Business Need Template, Establish Domain ppt, ...) | NMO | 2021-02-15 | Complete
| 2.2.5 | Plan Statistics Domain Way Ahead | Chris Carrino, SSullivan | 2021-01-28 | Complete | [7 empty] | Established a series of technical and business meetings.
| 2.2.5.1 | Develop( POA&M) | Nesbit, Rowland, SSullivan | 2021-03-30 | Past Due-on hold. | Contract Support issues transition to Domain postponed pending resolution | [6 empty] | Working with USCB to draft DSA, Define Value Proposition, develop POA&M, NBAC Brief and other administrative artifacts. PUT ON HOLD
| 2.2.5.2 | Review POA&M | NBAC Co-Chairs | 2021-04-30 | Planned
| 2.2.5.3 | Complete Business Need Document, develop value proposition | Nesbit, Rowland, SSullivan | 2021-04-30 | Past Due-on hold.
| 2.2.5.4 | Identify governance | Nesbit, Rowland, SSullivan | 2021-04-30 | Past Due-on hold.
| 2.2.3.5 | Draft DSA/Charter | Nesbit, Rowland, SSullivan | 2021-05-15 | Past Due-on hold.
| 2.2.5.6 | NBAC Recommendation | NBAC | 2021-05-30 | Past Due-on hold.
| 2.2.5.7 | ESC Endorsement | ESC | 2021-06-30 | Past Due-on hold.
| 2.2.5.8 | Stand up Domain | Doman Steward | 2021-06-30 | Past Due-on hold.
| 2.4 | VA Domain Kshemendra Paul, KEsocbar, SSullivan
| 2.3.1 | Scope, align effort at leadership level | Kshemendra Paul, Katherine Escobar | 2021-01-30 | Complete
| 2.3.2 | Provide Domain Onboarding Artifacts to VA (DSA template, POA&M strawman, How to docs, Busines Need Template, Establish Domain ppt, ...) | NMO | 2021-02-15 | Complete
| 2.3.3 | Plan VA Domain way ahead | VA/Katherine Escobar/Kamran Atri | 2021-04-30 | In Progress | Update
| 2.3.3.1 | Develop (POA&M) | VA/Kamran Atri | TBD
| 2.3.3.1 | Review POA&M | VA/Kamran Atri | TBD
| 2.3.3.2 | Complete Business Need Document, develop value proposition | VA/Kamran Atri | TBD
| 2.3.3.3 | Identify governance | VA/Kamran Atri | TBD
| 2.3.3.4 | Draft DSA/Charter | VA/Kamran Atri | TBD
| 2.3.3.5 | NBAC Recommendation | NBAC | TBD
| 2.3.3.6 | ESC Endorsement | ESC | TBD
|  | Stand up Domain | Domain Steward | TBD
| 2.4 | ADL "Learning & Development" Domain Sae Schatz, KEsocbar, Ssullivan, Katri
| 2.4.1 | Scope, align effort at leadership level | Schatz, KEscobar | 2021-01-30 | Complete
| 2.4.2 | Provide Domain Onboarding Artifacts to ADL (DSA template, POA&M strawman, How to docs, Busines Need Template, Establish Domain ppt, ...) | NMO | 2021-01-30 | Complete
| 2.4.3 | Plan ADL Domain way ahead | ADL/SSullivan | 2021-04-30 | Complete
| 2.4.3.1 | Develop (POA&M) | ADL/Ssullivan | 2021-01-30 | Complete
| 2.4.3.2 | Review POA&M | NBAC Co-Chairs | 2021-09-16 | Complete
| 2.4.3.3 | Complete Business Need Document, develop value proposition | ADL/SSullivan | 2021-09-16 | Complete
| 2.4.3.4 | Identify governance | ADL/SSullivan | 2021-09-16 | Complete
| 2.4.3.5 | Draft DSA/Charter | ADL/SSullivan | 2021-12-30 | In Progress | Signatures Pending for final DSA; final charter post kickoff
| 2.4.3.6 | NBAC Recommendation | NBAC | 2021-09-16 | Complete | Update
| 2.4.3.7 | ESC Endorsement | ESC | 2021-09-21 | Complete | Update
| 2.4.3.8 | Stand up Domain | Domain Steward | 2021-09-21 | Complete | Update
| 2.5 | IHS "International Human Services" Domain Michel Savoie, KEsocbar, Ssullivan, Katri, Tkrul
| 2.5.1 | Scope, align effort at leadership level | KAtri/TKrul/SSullivan | 2021-01-30 | Complete
| 2.5.2 | Provide Domain Onboarding Artifacts to ADL (DSA template, POA&M strawman, How to docs, Busines Need Template, Establish Domain ppt, ...) | NMO | 2021-01-30 | Complete
| 2.5.3 | Plan ADL Domain way ahead | KAtri/TKrul/SSullivan | 2021-04-30 | Complete
| 2.5.3.1 | Develop (POA&M) | KAtri/TKrul/SSullivan | 2021-01-30 | Complete
| 2.5.3.2 | Review POA&M | NBAC Co-Chairs | 2021-09-16 | Complete
| 2.5.3.3 | Complete Business Need Document, develop value proposition | KAtri/TKrul/SSullivan | 2021-09-16 | Complete
| 2.5.3.4 | Identify governance | KAtri/TKrul/SSullivan | 2021-09-16 | Complete
| 2.5.3.5 | Draft DSA/Charter | KAtri/TKrul/SSullivan | 2021-12-30 | In Progress | Signatures Pending for final DSA, final charter post kickoff
| 2.5.3.6 | NBAC Recommendation | NBAC | 2021-09-16 | Complete | Update
| 2.5.3.7 | ESC Endorsement | ESC | 2021-09-21 | Complete | Update
| 2.5.3.8 | Stand up Domain | Domain Steward | 2021-09-21 | Complete | Update
| 2.6 | Treasury Domain KEsocbar, SSullivan
| 2.6.1 | Scope, align effort at leadership level | Lisa Frank, Greg Midcap, KEscobar | 2021-01-30 | In Progress
| 2.6.2 | Provide Domain Onboarding Artifacts to Treasury (DSA template, POA&M strawman, How to docs, Busines Need Template, Establish Domain ppt, ...) | NMO | 2021-01-30 | Complete
| 2.6.3 | Plan Treasury Domain way ahead | Treasury,KEscobar | 2021-04-30 | In Progress
| 2.5.3.1 | Develop (POA&M) | Treasury,KEscobar | TBD
| 2.5.3.2 | Review POA&M | NBAC Co-Chairs | TBD
| 2.5.3.3 | Complete Business Need Document, develop value proposition | Treasury,KEscobar | TBD
| 2.5.3.4 | Identify governance | Treasury,KEscobar | TBD
| 2.5.3.5 | Draft DSA/Charter | Treasury,KEscobar | TBD
| 2.5.3.6 | NBAC Recommendation | NBAC | TBD
| 2.5.3.7 | ESC Endorsement | ESC | TBD
| 2.5.3.8 | Stand up Domain | Domain Steward | TBD | [8 empty] | Katherine v Kamran
| 2.3.6 | Introduce NIEM to DHS M&S COI | Syed Mohammad, Kamran Atri | Hold | Past Due/Issue | [7 empty] | Emailed Mohammad, no response
3. Support Domain Growth | 3.1 | Explore feasibility of initiating domain mentorship program | NBAC Co-Chairs, NBAC
| 3.1.1 | Schedule 2021 Planning Mtg | Kamran Atri, SSullivan | 2021-03-31 | Complete | [7 empty] | Template complete
| 3.2 | Plan Screening Domain way ahead | KEscobar | 2021-02-28 | In discussion with DHS CDO
4. Improve NIEM Implementation | 4.1 | NIEM Training | NBAC Co-Chairs, Katherine Escobar
| 4.1.1 | Provide NIEM Training (MilOps) | KEscobar, Webb Roberts | 1905-07-13 | Caronavirus impact
| 4.1.2 | Review and Update NIEM Training artifacts and approach | NBAC Co-Chairs | TBD | Past Due/Issue
| 4.1.3 | Identify NIEM Trainer candidates | KEscobar, Kamran Atri | TBD | Past Due/Issue
| 4.2 | NIEM Standard Designation | Katherine Escobar, SSullivan
| 4.2.1 | Acsert NIEM as a Voluntary Consenus Standard | KEscobar | 2021-03-30 | Complete
| 4.2.2 | Investigate becoming an OASIS Standard | KEscobar | 2021-03-30 | Complete | Briefed JUL ESC, scheduling one-on-one briefs with principals
| 4.2.3 | Brief COA/Proposal to NTAC, NBAC, ESC | KEscobar | 2021-09-21
| 4.2.4 | Transition Planing & Startup | KEscobar Lead | 2021-09-21 | In Progress | Transition adopted by ESC 9/21/21
5. Emerging Technologies Tiger Team (ET3) | 5.1 | Schedule 2021 ET3 Kickoff Mtg | JMapar, LMcNeill | 2021-01-18 | Complete
| 5.2 | Support/brief ET3 progress at Jan 19, 2021 ESC | JMapar, LMcNeill | 2021-01-19 | Complete
| 5.3 | Define ET3 "Next Steps" | JMapar, LMcNeill | TBD | Past Due/Issue
6. International Tiger Team | 6.1 | Plan ITT 2021 Activiites/Deliverables | Thomas Krull, Katherine Escobar
| 6 .1.1 | Schedule 2021 ITT Kickoff Mtg | Thomas Krul | 2021-05-30 | Past Due/Issue
| 6 .1.2 | Publish 2021 ITT POA&M | Thomas Krul | 2021-05-30 | Past Due/Issue
| 6.2 | Meet with Canadian Defense CDO Counterparts | Thomas Krul | 228/21 | Complete
7. State Local Tribal Tiger Team (SLT3) | 7.1 | Plan SLT_TT 2021 Activiites/Deliverables | SLTT Co-Chairs, Katherine Escobar
| 7 .1.1 | Indentify and instal replacement Co-Chairs | NBAC Co-Chairs, KEscobar | 2021-01-30 | Complete
| 7 .1.2 | Schedule NBAC Co-Chair/SLTTT Co-Chair Feb Collaborative Session | SSullivan | 2021-02-18 | Complete
| 7.1.3 | Announce new Co-Chairs to NBAC | NBAC Co-Chairs | 2021-02-25 | Complete
| 7 .1.4 | Schedule 2021 SLT_TT Kickoff Mtg | SLT_TT Co-Chairs | 2021-04-30 | Complete | [7 empty] | 19 April Kickoff
| 7 .1.5 | Publish 2021 SLT_TT POA&M | SLT_TT Co-Chairs | 2021-04-30 | Complete
| 7.2 | Meet with State of New Mexico government officials | SLT_TT Co-Chairs | 2021-02-26 | Complete
| 7.3 | National Association of State CIOs (NASCIO) Engagement | SLTT, Cait Ryan, Tom Carlson, Katherine Escobar
| 7.3.1 | Schedule webinar briefing(s) to NASCIO committee(s) | NBAC Co-Chairs,KEscobar | 2021-07-31 | In Progress
| 7.2.2 | Schedule webinar for State CDO Network | NBAC Co-Chairs,Tyler Kalykamp, KEscobar | 2021-07-31 | In Progress
8. NIEM Community Governance | 8.1 | Plan & Execute 2021 Annual Meeting | NBAC, NTAC, Katherine Escobar,Ralph O'Connell, SSullivan
| 8.1.1 | Schedule Planning Meeting | NBAC Co-Chairs, KEscobar, SSullivan | 2021-01-30 | Complete
| 8.1.2 | Propose tentative dates | NBAC Co-Chairs, KEscobar, SSullivan | 2021-01-30 | Complete
| 8.1.3 | Develop & publish POA&M | SSullivan | 2021-04-30 | Complete
| 8.2 | NBAC 2021 Annual Report | NBAC, NMO,SSullivan
| 8 .2.1 | Schedule Planning Meeting | NBAC Co-Chairs, KEscobar, SSullivan | 2021-09-30 | Planned
| 8 .2.2 | Develop & publish POA&M | SSullivan | 2021-10-30 | Planned
| 8.3 | Best of NIEM 2021 | KEscobar, NMO
| 8 .3.1 | Schedule Planning Meeting | NBAC Co-Chairs, KEscobar, SSullivan | 2021-06-30 | Complete
| 8.3.2 | Develop & publish POA&M | Swoodhouse | 2021-07-30 | Complete
| 8.4 | Update NBAC Governance Docs | NBAC, NMO
| 8.4.1 | Update NBAC SOP | NBAC, NTAC, NMO | 2021-10-30 | Planned
| 8.4.2 | Update NBAC Charter | NBAC, NTAC, NMO | 2021-10-30 | Planned
9. 2022 Work Plan | 9.1 | Plan NIEM 2022 Work Plan | NBAC, NTAC, SSullivan,KEscobar
| 9.1.1 | Schedule NTAC. NBAC, NMO Work Plan Collaboration | NBAC, NTAC, NMO | 2021-10-21 | Complete | ICW Annual Meeting